## Sheet1
Test Report of Project Name | PI2 | [16 empty] | Not Started
Updated by: | Lisa |  |  |  | Updated on: | [12 empty] | WIP
[6 empty] | #VALUE! | [11 empty] | Complete
Test Execution Status | [17 empty] | Cancelled
Scope Item | Planned Signoff Date | Actual Signoff Date | Test Cycles |  | Test Type | Planned Delivery Date | Actual Delivery Date | Test Start Date | Duration (days) | Status | Planned Test Cases |  | Passed Test Cases | Failed Test Cases | Blocked Test Cases | Deferred Test Cases | Pass Rate (%)
ETL1 |  |  | C1 |  | Functionality |  |  | 2018-09-12 | 12 | Complete | 350 |  | 344 | 6 |  |  | 98.29%
|  |  | C2 |  | Re-Test fixes |  |  | 2018-09-24 | 4 | Complete | 350 |  | 348 | 2 |  |  | 99.43%
|  |  | C3 |  | Re-Test fixes |  |  | 2018-10-01 | 2 | Complete | 350 |  | 350 | 3 |  |  | 100%
Exporting CSV file |  |  | C1 |  | Functionality |  |  | 2018-10-05 | 5 | Complete | 100 |  | 98 |  |  |  | 98%
|  |  | C2 |  | Re-Test fixes | [11 empty] | #DIV/0!
Report validation per customer |  |  | C1 |  | Functionality |  |  | 2018-10-03 | 15 | Complete | 1800 |  | 1710 |  |  |  | 95%
|  |  | C2 |  | Re-Test fixes |  |  | 2018-10-23 | 30 | WIP | 1800 | [5 empty] | 0%
Defect Management
Scope Item | ETL |  |  |  |  | Exporting CSV files |  |  |  | Report validation per customer
Defect Severity | Reported | Open | Ready for QA | In Progress | Closed | Reported | Open | Ready for QA | Closed | Reported | Open | In progerss | Ready for QA | Closed
Blocker |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Critical |  |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Major | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 21 | 10 | 5 |  | 6
Minor | 3 | 1 |  |  | 2 | 0 | 0 | 0 | 0 | 3 | 2 |  |  | 1
Total: | 8 | 2 | 2 |  | 3 | 1 | 1 | 0 | 0 | 24 | 12 | 5 | 0 | 7
17 questions
0
Note on N9: Lisa Ke: duplicate records need to verify after exporting to CSV files
Note on N11: Lisa Ke: duplicate records need to verify after exporting to CSV files